## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Set up development environment using WSL, Docker and Astro CLI | MUST HAVE | System setup |  | 3- Completed
S1 | S1 | US-002 | Create ETL project structure | MUST HAVE | US-001 |  | 3- Completed
S1 | S1 | US-003 | Install and configure Apache Airflow | MUST HAVE | US-001 |  | 3- Completed
S2 | S2 | US-004 | Extract cryptocurrency dataset from CSV | MUST HAVE | US-003 |  | 3- Completed
S2 | S2 | US-005 | Clean missing values and remove duplicates | MUST HAVE | US-004 |  | 3- Completed
S2 | S2 | US-006 | Apply transformations using Pandas | MUST HAVE | US-005 |  | 3- Completed
S3 | S3 | US-007 | Create Airflow DAG for ETL pipeline | MUST HAVE | US-006 |  | 3- Completed
S3 | S3 | US-008 | Implement logging and monitoring | SHOULD HAVE | US-007 |  | 3- Completed
S4 | S4 | US-009 | Create aggregated dataset and moving averages | MUST HAVE | US-008 |  | 3- Completed
S4 | S4 | US-010 | Build dashboard using Streamlit or Dash | COULD HAVE | US-009 |  | 3- Completed
S4 | S4 | US-011 | Deploy ETL pipeline and test with large dataset | MUST HAVE | US-010 |  | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 41 | 9 | 9 | 8 | 6 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-01 | Install WSL | 2026-02-04 | 2026-02-06 | Revati | Setup | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-02 | Install Docker | 2026-02-10 | 2026-02-13 | Revati | Setup | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-03 | Create project structure | 2026-02-16 | 2026-02-20 | Krishni | Development | 3-Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-04 | Install Astro CLI and Airflow | 2026-02-23 | 2026-02-25 | Krishni | Setup | 3-Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-05 | Load CSV dataset | 2026-02-26 | 2026-02-27 | Charanya | Development | 3-Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-06 | Handle missing values | 2026-03-02 | 2026-03-10 | Revati | Data Cleaning | 3-Completed | 7 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-07 | Apply transformations | 2026-03-11 | 2026-03-19 | Charanya | Development | 3-Completed | 8 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-08 | Create Airflow DAG | 2026-03-20 | 2026-03-28 | Krishni | Development | 3-Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Docker installation issue | Restarted Docker and verified installation
Sprint 1 | Day 5 | Airflow not starting | Enabled Docker TCP setting and restarted Astro
Sprint 2 | Day 10 | Dataset format mismatch | Converted timestamp to datetime format
Sprint 2 | Day 14 | Missing values in dataset | Applied data cleaning rules using Pandas
Sprint 3 | Day 17 | DAG not triggering | Restarted Astro environment
Sprint 3 | Day 21 | Logs not visible | Configured Airflow logging module

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-06 | 2026-02-09 | Krishni | Better environment documentation | Delaying setup | Team collaboration | Documented setup steps
2 | Sprint 2 | 2026-02-13 | 2026-02-15 | Charanya | Automated data cleaning | Manual data checks | Code reviews | Implemented Pandas scripts
3 | Sprint 3 | 2026-03-01 | 2026-03-05 | Revati | Better monitoring | Ignoring logs | Using Airflow DAGs | Added logging module
4 | Sprint 4 | 2026-03-15 | 2026-03-18 | Krishni | Dashboard integration | Unstructured testing | Pipeline automation | Planned Streamlit dashboard